## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | As a Data Engineer, I want to gather historical visa datasets and handle missing values or noise so that the data is clean and ready for analysis | Must Have | Dataset availability | Individuals | Completed
Sprint 2 | Sprint 2 | US002 | As a Data Scientist, I want to perform exploratory data analysis to understand patterns and trends in visa application data | Must Have | Preprocessed and Cleaned data | Individuals | Completed
Sprint 3 | Sprint 3 | US003 | As an AI developer, I want to train and evaluate machine learning models for the reliability and accuracy of visa predictions | Must Have | Feature Engineering and EDA | Individuals | Completed
Sprint 4 | Sprint 4 | US004 | As a Frontend developer, I want to design an intuitive input form so that users can easily enter their visa application details | Must Have | Backend API and Trained ML Models | Individuals | In process

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US001 | T1 | Collect visa dataset with application & decision dates from public sources (Kaggle / data.gov / synthetic data) | 02-Feb-2026 | 05-Feb-2026 | Backend1 | Data Collection | Done | 6 | bar: Day 1 to Day 2
US001 | T2 | Explore visa dataset structure, review all attributes, understand column definitions and data types | 06-Feb-2026 | 09-Feb-2026 | Backend2 | Data Exploration | Done | 4 | bar: Day 3 to Day 4
US001 | T3 | Clean dataset: handle missing values using mean/mode imputation, remove duplicate records and fix inconsistent formats | 10-Feb-2026 | 13-Feb-2026 | Backend3 | Data Cleaning | Done | 8 | bar: Day 5 to Day 9
US001 | T4 | Preprocess data: encode categorical variables (visa type, country, office) and compute target variable (processing days) | 14-Feb-2026 | 16-Feb-2026 | Backend4 | Data Preprocessing | Done | 6 | bar: Day 10 to Day 13
SPRINT 2 BACKLOG ¦ Exploratory Data Analysis & Feature Engineering
US002 | T5 | Perform EDA using visualizations: plot processing time distributions across visa types and applicant regions (Matplotlib / Seaborn) | 17-Feb-2026 | 20-Feb-2026 | Backend1 | EDA | Done | 8 | bar: Day 1 to Day 3
US002 | T6 | Identify outliers in dataset, analyse seasonal and regional processing time trends, improve data quality before modelling | 21-Feb-2026 | 24-Feb-2026 | Backend2 | EDA | Done | 6 | bar: Day 4 to Day 7
US002 | T7 | Create new features for analysis: seasonal index, country-level average wait time, office workload score and applicant category flags | 25-Feb-2026 | 01-Mar-2026 | Backend3 | Feature Engineering | Done | 10 | bar: Day 8 to Day 12
SPRINT 3 BACKLOG ¦ Predictive Modelling
US003 | T8 | Train Linear Regression baseline model for visa processing time prediction; validate assumptions and check for multicollinearity | 02-Mar-2026 | 05-Mar-2026 | Backend1 | Model Training | Done | 8 | bar: Day 1 to Day 3
US003 | T9 | Train Random Forest regression model; resolve model selection confusion by comparing multiple algorithms side by side | 06-Mar-2026 | 09-Mar-2026 | Backend2 | Model Training | Done | 12 | bar: Day 4 to Day 8
US003 | T10 | Evaluate all trained models using MAE, RMSE and R² score; generate comparison table and select best-performing model | 10-Mar-2026 | 13-Mar-2026 | Backend3 | Model Evaluation | Done | 6 | bar: Day 9 to Day 11
US003 | T11 | Fine-tune hyperparameters of selected best model using RandomizedSearchCV; serialise final model with pickle for API integration | 14-Mar-2026 | 15-Mar-2026 | Backend4 | Model Optimisation | Done | 8 | bar: Day 12 to Day 14
SPRINT 4 BACKLOG ¦ Web App & Deployment
US004 | T12 | Implement frontend with input form | 16-Mar-2026 | 20-Mar-2026 | Frontend1 | UI Development | To Do
US004 | T13 | Connect backend prediction engine | 21-Mar-2026 | 24-Mar-2026 | Backend1 | Integration | To Do
US004 | T14 | Deploy on cloud (Azure/AWS/Heroku) | 25-Mar-2026 | 28-Mar-2026 | Both Team | Deployment | To Do
US004 | T15 | Final testing with multiple sample cases | 29-Mar-2026 | 30-Mar-2026 | Both Team | Testing | To Do

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 3 | Difficulty in understanding visa dataset structure | Reviewed dataset attributes and performed dataset exploration
Sprint 2 | Day 4 | Missing values and preprocessing issues in dataset | Cleaned dataset and handled missing values using preprocessing techniques
Sprint 3 | Day 3 | Confusion in selecting suitable machine learning model | Implemented Linear Regression and Random Forest models fro prediction
Sprint 4 | Day 3 | Difficulty evaluting model performance and preparing results | Calculated MSE, RMSE ,MAE and finalized project documentation

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint1 | 2026-02-01 | 2026-02-01 | Individuals | Collect visa dataset with application & decision dates. Clean dataset and handle missing values | Using incomplete datasets. Ignoring data preprocessing | Team discussion for dataset selection. Documenting preprocessing steps | Collected visa dataset and performed data cleaning and preprocessing.
2 | Sprint2 | 2026-02-01 | 2026-03-01 | Individuals | Perform EDA using visualizations. Create new features for analysis | Ignoring outliers in dataset. Running analysis without visualization | Sharing analysis results with team. Improving data quality | Conducted EDA with visualizations and created new features for analysis.
3 | Sprint3 | 2026-03-01 | 2026-03-01 | Individuals | Train ML models for visa prediction. Evaluate models using MAE and RMSE | Using only one model.Skipping model evaluation | Testing model accuracy. Sharing progress in standup meetings | Trained machine learning models and evaluated performance using MAE and RMSE.
4 | Sprint4 | 2026-03-01 | 2026-03-01 | Individuals | Develop web app for prediction. Connect frontend with ML model | Stop delaying integration tasks. Stop making unplanned code changes | Continue team coordination. Continue testing model results | Planned development of web application and integration of prediction model.
5
6
7